## Jira Backlog
Issue ID | Issue Type | Summary | Description | Priority | Story Points | Parent Issue | Sprint | Assignee | Dependencies | SRS Requirement(s) | Acceptance Criteria
EPIC-01 | Epic | User Authentication | Enable secure user account access | High |  |  | Sprint 1 | Poojitha P |  | REQ-22 | User authentication is required for access to user accounts.
US-01 | Story | User Registration | As a user, I want to register so that I can create an account and access the quiz system. | High | 5 | EPIC-01 | Sprint 1 | Nakshathira | TASK-01, TASK-02 | REQ-22 | Registration form is available; valid details create an account; invalid input is rejected.
TASK-01 | Task | Design registration/login UI | Create the registration and login screens with clear input fields and messages. | High | 3 | US-01 | Sprint 1 | Poojitha P |  | REQ-22 | Registration and login screens are implemented and usable.
TASK-02 | Task | Implement authentication | Implement account authentication and validation for user access. | High | 5 | US-01 | Sprint 1 | Poojitha P |  | REQ-22 | Valid users can authenticate; invalid credentials are rejected.
US-02 | Story | User Login | As a user, I want to log in securely so that I can access my account. | High | 5 | EPIC-01 | Sprint 1 | Nakshathira | TASK-03 | REQ-22 | Successful login grants access; unauthorized users cannot access protected account functions.
TASK-03 | Task | Test authentication | Test valid, invalid, and unauthorized login scenarios. | High | 3 | US-02 | Sprint 1 | Nakshathira |  | REQ-22 | All defined authentication scenarios pass.
EPIC-02 | Epic | Quiz Category & Selection | Allow users to discover and select quizzes | High |  |  | Sprint 1 | Sharanya N |  | REQ-01, REQ-02, REQ-03 | Available categories and quizzes can be displayed and selected.
US-03 | Story | View Quiz Categories | As a user, I want to view available categories so that I can choose a quiz area. | High | 3 | EPIC-02 | Sprint 1 | Sharanya N | TASK-04 | REQ-01 | Available quiz categories are displayed correctly.
TASK-04 | Task | Create category interface | Create the interface for displaying available quiz categories. | High | 3 | US-03 | Sprint 1 | Sharanya N |  | REQ-01 | Categories are clearly displayed and selectable.
US-04 | Story | Select Quiz Category | As a user, I want to select a quiz category so that I can access quizzes in that category. | High | 3 | EPIC-02 | Sprint 1 | Sharanya N | TASK-05 | REQ-02 | User can select a category and the selected category is retained.
TASK-05 | Task | Implement category selection | Connect category selection to quiz retrieval. | High | 3 | US-04 | Sprint 1 | Sharanya N |  | REQ-02 | Selecting a category displays its associated quizzes.
US-05 | Story | View Available Quizzes | As a user, I want to view quizzes under a selected category so that I can choose one. | High | 3 | EPIC-02 | Sprint 1 | Poojitha P | TASK-06 | REQ-03 | Quizzes associated with the selected category are displayed.
TASK-06 | Task | Implement quiz listing | Retrieve and display quizzes for the selected category. | High | 3 | US-05 | Sprint 1 | Rahul Rajkumar S |  | REQ-03 | Correct quizzes are shown for the selected category.
EPIC-03 | Epic | Timed Quiz | Allow users to attempt MCQ quizzes within a time limit | High |  |  | Sprint 2 | Rahul Rajkumar S |  | REQ-04, REQ-05, REQ-06, REQ-07, REQ-08 | Questions, options, timer, response recording, and timeout behavior are supported.
US-06 | Story | Display Quiz Questions | As a user, I want to see multiple-choice questions and options so that I can answer the quiz. | High | 5 | EPIC-03 | Sprint 2 | Rahul Rajkumar S | TASK-07 | REQ-04, REQ-05 | Selected quiz displays its questions and multiple answer options.
TASK-07 | Task | Build quiz interface | Create the quiz screen for questions, options, navigation, and remaining time. | High | 5 | US-06 | Sprint 2 | Rahul Rajkumar S |  | REQ-04, REQ-05 | Quiz questions and multiple options are displayed clearly.
US-07 | Story | Start Quiz Timer | As a user, I want the timer to start when the quiz begins so that the time limit is enforced. | High | 5 | EPIC-03 | Sprint 2 | Rahul Rajkumar S | TASK-08 | REQ-06 | Timer starts when quiz starts and displays remaining time.
TASK-08 | Task | Implement countdown timer | Implement the quiz countdown and expiration logic. | High | 5 | US-07 | Sprint 2 | Poojitha P |  | REQ-06, REQ-08 | Timer counts down correctly and triggers quiz end at zero.
US-08 | Story | Record Answers | As a user, I want my selected answers recorded so that they can be evaluated. | High | 5 | EPIC-03 | Sprint 2 | Poojitha P | TASK-09 | REQ-07 | Selected answers are retained for evaluation.
TASK-09 | Task | Implement answer recording | Store selected answers during the quiz session. | High | 5 | US-08 | Sprint 2 | Poojitha P |  | REQ-07 | Each submitted selection is recorded against the relevant question.
US-09 | Story | Automatic Quiz Submission | As a user, I want the quiz to end automatically when time expires. | High | 5 | EPIC-03 | Sprint 2 | Nakshathira | TASK-10 | REQ-08 | Quiz automatically ends at time expiry and no additional responses are accepted.
TASK-10 | Task | Implement timeout submission | Trigger quiz submission when the timer reaches zero. | High | 3 | US-09 | Sprint 2 | Nakshathira |  | REQ-08 | Expired quiz is submitted and further responses are blocked.
EPIC-04 | Epic | Scoring & Instant Feedback | Evaluate answers and show results | High |  |  | Sprint 3 | Poojitha P |  | REQ-09, REQ-10, REQ-11, REQ-12 | Answers are evaluated, feedback is provided, and final score is displayed.
US-10 | Story | Evaluate Answers | As a user, I want my submitted answers evaluated so that I know which answers are correct. | High | 5 | EPIC-04 | Sprint 3 | Sharanya N | TASK-11 | REQ-09 | Submitted answers are compared with correct answers.
TASK-11 | Task | Implement answer evaluation | Implement correct-answer comparison for submitted responses. | High | 5 | US-10 | Sprint 3 | Poojitha P |  | REQ-09 | Each submitted answer is evaluated correctly.
US-11 | Story | Instant Feedback | As a user, I want feedback on my answers so that I can understand my performance. | High | 3 | EPIC-04 | Sprint 3 | Poojitha P | TASK-12 | REQ-10 | Appropriate feedback is shown after response or completion.
TASK-12 | Task | Implement feedback display | Display appropriate feedback based on answer evaluation. | High | 3 | US-11 | Sprint 3 | Sharanya N |  | REQ-10 | Feedback is displayed correctly.
US-12 | Story | Calculate Score | As a user, I want my score calculated based on correct answers. | High | 5 | EPIC-04 | Sprint 3 | Rahul Rajkumar S | TASK-13 | REQ-11 | Score matches the number of correct answers.
TASK-13 | Task | Implement score calculation | Calculate final quiz score from evaluated answers. | High | 5 | US-12 | Sprint 3 | Rahul Rajkumar S |  | REQ-11 | Correct answers contribute accurately to the final score.
US-13 | Story | Display Final Result | As a user, I want to see my final score after completing the quiz. | High | 3 | EPIC-04 | Sprint 3 | Rahul Rajkumar S | TASK-14 | REQ-12 | Final score is displayed after completion.
TASK-14 | Task | Create result screen | Create the result page with score and relevant feedback. | High | 3 | US-13 | Sprint 3 | Rahul Rajkumar S |  | REQ-12 | Result screen displays the correct final score.
EPIC-05 | Epic | Leaderboard & Performance | Store results and display rankings | Medium |  |  | Sprint 3 | Sharanya N |  | REQ-13, REQ-14, REQ-15 | Completed results are stored and rankings are displayed.
US-14 | Story | Store Quiz Results | As a user, I want my quiz result stored so that my performance can be retrieved. | Medium | 5 | EPIC-05 | Sprint 3 | Sharanya N | TASK-15 | REQ-13 | Completed quiz score is stored accurately.
TASK-15 | Task | Implement result storage | Store user, quiz, score, and attempt information. | Medium | 5 | US-14 | Sprint 3 | Sharanya N |  | REQ-13 | Result record is created after quiz completion.
US-15 | Story | Maintain Leaderboard | As a system, I want leaderboard records maintained for completed quizzes. | Medium | 5 | EPIC-05 | Sprint 3 | Nakshathira | TASK-16 | REQ-14 | Leaderboard data is maintained from recorded results.
TASK-16 | Task | Implement leaderboard logic | Retrieve and organize relevant quiz scores for rankings. | Medium | 5 | US-15 | Sprint 3 | Nakshathira |  | REQ-14, REQ-15 | Rankings are generated from recorded performance.
US-16 | Story | View Leaderboard | As a user, I want to view rankings so that I can compare quiz performance. | Medium | 3 | EPIC-05 | Sprint 3 | Poojitha P | TASK-17 | REQ-15 | Leaderboard displays user rankings based on performance.
TASK-17 | Task | Create leaderboard UI | Create the leaderboard screen and display ranking data. | Medium | 3 | US-16 | Sprint 3 | Nakshathira |  | REQ-15 | Leaderboard is readable and correctly ordered.
EPIC-06 | Epic | Quiz Content Management | Allow administrators to manage quiz content | Medium |  |  | Sprint 4 | Nakshathira |  | REQ-16, REQ-17, REQ-18, REQ-19 | Authorized administrators can manage questions and categories.
US-17 | Story | Add Quiz Questions | As an administrator, I want to add quiz questions so that quiz content can be created. | Medium | 5 | EPIC-06 | Sprint 4 | Nakshathira | TASK-18 | REQ-16 | Administrator can add valid quiz questions.
TASK-18 | Task | Implement question creation | Create admin functionality to add questions and answer options. | Medium | 5 | US-17 | Sprint 4 | Nakshathira |  | REQ-16 | New questions are validated and stored.
US-18 | Story | Update Quiz Questions | As an administrator, I want to update questions so that quiz content remains accurate. | Medium | 5 | EPIC-06 | Sprint 4 | Rahul Rajkumar S | TASK-19 | REQ-17 | Administrator can edit existing questions.
TASK-19 | Task | Implement question editing | Create admin functionality for updating existing questions. | Medium | 5 | US-18 | Sprint 4 | Poojitha P |  | REQ-17 | Updated question data is saved correctly.
US-19 | Story | Delete Quiz Questions | As an administrator, I want to delete questions so that outdated content can be removed. | Medium | 3 | EPIC-06 | Sprint 4 | Poojitha P | TASK-20 | REQ-18 | Administrator can delete a question after confirmation.
TASK-20 | Task | Implement question deletion | Add delete functionality with appropriate validation/confirmation. | Medium | 3 | US-19 | Sprint 4 | Poojitha P |  | REQ-18 | Selected question is removed and no longer appears in quizzes.
US-20 | Story | Manage Quiz Categories | As an administrator, I want to manage categories so that quiz content can be organized. | Medium | 5 | EPIC-06 | Sprint 4 | Sharanya N | TASK-21 | REQ-19 | Administrator can create/update/delete categories as supported by the system.
TASK-21 | Task | Implement category management | Create admin functions for maintaining quiz categories. | Medium | 5 | US-20 | Sprint 4 | Sharanya N |  | REQ-19 | Category changes are validated and stored.
EPIC-07 | Epic | Security & Access Control | Protect accounts, administrative functions, and sensitive data | High |  |  | Sprint 4 | Poojitha P |  | REQ-22, REQ-23, REQ-24 | Authentication, admin authorization, and protected transmission are supported.
US-21 | Story | Restrict Admin Functions | As an administrator, I want administrative functions restricted to authorized administrators. | High | 5 | EPIC-07 | Sprint 4 | Poojitha P | TASK-22 | REQ-23 | Non-admin users cannot access administrative functions.
TASK-22 | Task | Implement role-based access | Restrict admin pages/actions based on authorization. | High | 5 | US-21 | Sprint 4 | Poojitha P |  | REQ-23 | Unauthorized access attempts are denied.
US-22 | Story | Protect Sensitive Data | As a user, I want my credentials and sensitive information protected during transmission. | High | 5 | EPIC-07 | Sprint 4 | Rahul Rajkumar S | TASK-23 | REQ-24 | Sensitive information is transmitted using protected communication.
TASK-23 | Task | Configure secure communication | Configure HTTPS/protected communication as supported by deployment environment. | High | 5 | US-22 | Sprint 4 | Rahul Rajkumar S |  | REQ-24 | Sensitive data is not transmitted through unprotected application communication.
EPIC-08 | Epic | Performance & Reliability | Ensure responsive and accurate normal operation | Medium |  |  | Sprint 4 | Rahul Rajkumar S |  | REQ-20, REQ-21 | Quiz actions and result recording operate with minimal noticeable delay and accurate data.
US-23 | Story | Responsive Quiz Operation | As a user, I want quiz actions to respond with minimal delay during normal operation. | Medium | 3 | EPIC-08 | Sprint 4 | Poojitha P | TASK-24 | REQ-20 | Quiz questions and user actions respond with minimal noticeable delay.
TASK-24 | Task | Performance testing | Test quiz loading and user actions under normal operating conditions. | Medium | 3 | US-23 | Sprint 4 | Rahul Rajkumar S |  | REQ-20 | Normal-operation performance meets the SRS expectation.
US-24 | Story | Accurate Result Recording | As a user, I want my responses and scores recorded accurately without noticeable delay. | Medium | 3 | EPIC-08 | Sprint 4 | Sharanya N | TASK-25 | REQ-21 | Responses and scores are stored accurately.
TASK-25 | Task | Reliability testing | Test response recording and score storage for accuracy and normal-operation failures. | Medium | 3 | US-24 | Sprint 4 | Sharanya N |  | REQ-21 | Stored responses and scores match the submitted quiz data.

## Team Details
Field | Value | SRN
Team Number | 73
Project | Online Quiz System
Member 1 | Nakshathira | PES2UG24AM096
Member 2 | Poojitha P | PES2UG24AM112
Member 3 | Sharanya N | PES2UG24AM150
Member 4 | Rahul Rajkumar S | PES2UG24AM128

## Sprint Plan
Sprint | Goal | Epics | Scope
Sprint 1 | Authentication + Category & Quiz Selection | EPIC-01, EPIC-02 | Core access and quiz discovery
Sprint 2 | Timed Quiz | EPIC-03 | Question display, timer, answer recording, timeout
Sprint 3 | Scoring + Leaderboard | EPIC-04, EPIC-05 | Evaluation, feedback, results, rankings
Sprint 4 | Admin + Security + Reliability | EPIC-06, EPIC-07, EPIC-08 | Content management, access control, performance/reliability

## Requirement Mapping
Requirement ID | Requirement | Mapped User Story | Sprint
REQ-01 | Display available quiz categories | US-03 | Sprint 1
REQ-02 | Allow user to select quiz category | US-04 | Sprint 1
REQ-03 | Display quizzes associated with selected category | US-05 | Sprint 1
REQ-04 | Display multiple-choice questions | US-06 | Sprint 2
REQ-05 | Provide multiple answer options | US-06 | Sprint 2
REQ-06 | Start timer when quiz begins | US-07 | Sprint 2
REQ-07 | Record selected answers | US-08 | Sprint 2
REQ-08 | Automatically end quiz when time expires | US-09 | Sprint 2
REQ-09 | Evaluate submitted answers | US-10 | Sprint 3
REQ-10 | Provide instant feedback | US-11 | Sprint 3
REQ-11 | Calculate score based on correct answers | US-12 | Sprint 3
REQ-12 | Display final score | US-13 | Sprint 3
REQ-13 | Store user's quiz score | US-14 | Sprint 3
REQ-14 | Maintain leaderboard records | US-15 | Sprint 3
REQ-15 | Display user rankings | US-16 | Sprint 3
REQ-16 | Allow administrator to add questions | US-17 | Sprint 4
REQ-17 | Allow administrator to update questions | US-18 | Sprint 4
REQ-18 | Allow administrator to delete questions | US-19 | Sprint 4
REQ-19 | Allow administrator to manage categories | US-20 | Sprint 4
REQ-20 | Minimal delay during normal operation | US-23 | Sprint 4
REQ-21 | Accurate response and score recording | US-24 | Sprint 4
REQ-22 | Authentication for user accounts | US-01, US-02 | Sprint 1
REQ-23 | Restrict admin functions to authorized administrators | US-21 | Sprint 4
REQ-24 | Protect credentials and sensitive information during transmission | US-22 | Sprint 4