## Sheet1
Issue ID | Issue Type | Summary | Description | Priority | Story Points | Parent Issue | Sprint | Assignee | Dependencies | SRS Requirement(s) | Acceptance Criteria
S1-01 | Task | Set Up Database Schema | Create the structured database required to store users, quiz categories, quizzes, questions, answers, and results. | High | 5 | Sprint 1 – Core Quiz System | Sprint 1 | Poojitha | None | 7.1 Database Requirements; ER Diagram | Database schema is created according to the SRS data model; required entities and relationships are implemented; data can be stored and retrieved reliably.
S1-02 | Story | Implement User Authentication | Implement registration and login functionality for users through the authentication interface. | High | 5 | Sprint 1 – Core Quiz System | Sprint 1 | Poojitha | S1-01 | REQ-22; Section 3.1 User Interfaces | Users can register/login successfully; invalid credentials are rejected; authentication is required before protected functionality is accessed.
S1-03 | Story | Display Quiz Categories | Display the available quiz categories when the user opens the quiz system. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Poojitha | S1-01 | REQ-01 | The system retrieves and displays available quiz categories correctly.
S1-04 | Story | Select Quiz Category | Allow the user to select a quiz category. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Poojitha | S1-03 | REQ-02 | The user can select a category and the selected category is correctly identified by the system.
S1-05 | Story | Display Quizzes for Selected Category | Display the quizzes available under the category selected by the user. | High | 5 | Sprint 1 – Core Quiz System | Sprint 1 | Poojitha | S1-04 | REQ-03 | The system displays quizzes associated with the selected category and retrieves the quiz information correctly.
S1-06 | Story | Display Quiz Questions and Options | Display multiple-choice questions and answer options for the selected quiz. | High | 5 | Sprint 1 – Core Quiz System | Sprint 1 | Poojitha | S1-05 | REQ-04, REQ-05 | The selected quiz displays its questions and required answer options correctly.
S1-07 | Story | Start Quiz Timer | Start the quiz timer when the user begins the quiz and display the remaining time. | High | 5 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-06 | REQ-06; Section 3.1 User Interfaces | The timer starts when the quiz begins; remaining time is visible; timer follows the quiz time limit.
S1-08 | Story | Record User Answers | Record the answers selected by the user while attempting the quiz. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-06 | REQ-07 | User selections are recorded correctly and remain available for submission.
S1-09 | Story | End Quiz on Timeout | Automatically end the quiz when the specified time limit expires. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-07, S1-08 | REQ-08 | The quiz automatically ends when the timer reaches the limit and no additional answers are accepted.
S1-10 | Story | Evaluate Submitted Answers | Compare submitted answers with the correct answers and determine which responses are correct. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-08 | REQ-09 | Each submitted answer is evaluated against the correct answer accurately.
S1-11 | Story | Provide Instant Feedback | Provide feedback to the user based on submitted answers or completion of the quiz. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-10 | REQ-10 | Feedback is displayed appropriately and corresponds to the evaluated answer.
S1-12 | Story | Calculate Quiz Score | Calculate the user's final score based on the number of correct answers. | High | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-10 | REQ-11 | The score is calculated accurately from the user's correct answers.
S1-13 | Story | Display Final Score | Display the calculated final score after the quiz is completed. | High | 2 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-12 | REQ-12 | The final score is displayed after quiz completion and matches the calculated score.
S1-14 | Task | Validate Performance and Reliable Response Handling | Verify that quiz questions, user actions, responses, and scores are processed with minimal delay and without noticeable errors under normal operation. | Medium | 3 | Sprint 1 – Core Quiz System | Sprint 1 | Nakshathira | S1-09, S1-13 | REQ-20, REQ-21 | Questions and user actions respond with minimal delay; responses and scores are recorded accurately without noticeable delay.
S2-01 | Story | Store Quiz Results | Store the user's completed quiz score and related result information in the database after quiz completion. | High | 5 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S1-13 | REQ-13; 7.1 Database Requirements | Completed quiz results are stored correctly; stored result data can be retrieved without loss or corruption.
S2-02 | Story | Maintain Leaderboard Records | Maintain leaderboard records using the recorded results of completed quizzes. | Medium | 5 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S2-01 | REQ-14 | The system maintains leaderboard records for completed quizzes and updates them when new valid results are stored.
S2-03 | Story | Display Leaderboard Rankings | Display users' rankings based on their recorded quiz performance. | Medium | 3 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S2-02 | REQ-15 | Leaderboard rankings are displayed correctly based on recorded quiz performance.
S2-04 | Task | Implement Quiz Result Report | Provide the quiz result information required by the SRS report layout, including user name, quiz title, category, score, time taken, and attempt date. | Medium | 5 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S2-01 | Appendix B – Quiz Result Report | Quiz result displays all required report fields; values correspond to the completed quiz attempt.
S2-05 | Task | Test Result Persistence and Leaderboard Accuracy | Verify that completed quiz results remain accurate and that leaderboard data is generated from recorded quiz performance. | Medium | 3 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S2-01, S2-03 | REQ-21; 7.3 Data Management Requirements | Stored scores remain accurate and consistent; leaderboard information reflects recorded results correctly.
S2-06 | Story | Authorize Administrator Access | Restrict administrative functions so that only authorized administrators can access quiz content management. | High | 5 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S1-02, S2-05 | REQ-23; 2.3 User Classes and Characteristics | Only authorized administrators can access administrative functions; normal users cannot access restricted management operations.
S2-07 | Task | Validate Safety and Data Consistency | Verify that submitted answers and quiz results are not improperly lost and that expired quiz sessions do not accept additional responses. | High | 3 | Sprint 2 – Results and Administration | Sprint 2 | Rahul | S1-09, S2-01 | 6.2 Safety Requirements; 7.3 Data Management Requirements | Submitted answers and quiz results are retained during normal operation; expired sessions reject further responses; stored data remains accurate and consistent.
Issue ID | Issue Type | Summary | Description | Priority | Story Points | Parent Issue | Sprint | Assignee | Dependencies | SRS Requirement(s) | Acceptance Criteria
S2-08 | Story | Add Quiz Questions | Allow the administrator to add new quiz questions and required answer information. | Medium | 5 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-06 | REQ-16 | The administrator can add valid quiz questions; new questions are stored correctly in the database.
S2-09 | Story | Update Quiz Questions | Allow the administrator to modify existing quiz questions and answer information. | Medium | 3 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-08 | REQ-17 | The administrator can update existing questions; updated information is stored and displayed correctly.
S2-10 | Story | Delete Quiz Questions | Allow the administrator to remove existing quiz questions. | Medium | 3 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-08 | REQ-18 | The administrator can delete questions; deleted questions no longer appear in available quiz content.
S2-11 | Story | Manage Quiz Categories | Allow the administrator to manage quiz categories used by the system. | Medium | 5 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-06 | REQ-19 | The administrator can add, update, or remove quiz categories as required; category data remains consistent.
S2-12 | Task | Protect Credentials and Sensitive Data | Ensure user credentials and sensitive information are protected during client-server communication using secure communication practices. | High | 3 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-06 | REQ-24; 3.3 Communications Interfaces | User credentials and sensitive information are protected during transmission; secure communication is used where supported by the system.
S2-13 | Task | Validate Responsive Browser Compatibility | Verify that the completed system provides a consistent user experience across commonly used desktop and mobile web browsers. | Medium | 3 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-11 | 6.4 Software Quality Attributes; 7.2 Compatibility Requirements | The application remains usable and consistent across supported desktop and mobile browsers.
S2-14 | Task | Final System Integration and Testing | Integrate all completed functionality with the existing product and perform final verification against the SRS and Test Plan. | High | 5 | Sprint 2 – Results and Administration | Sprint 2 | Sharanya | S2-10, S2-11, S2-12, S2-13 | Software Quality Attributes; Testability Requirements | The complete system works end-to-end; integrated features pass verification; no critical defects remain; requirements are traceable to implemented functionality.

## Sheet2
Sprint | Goal | Epics | Scope
Sprint 1 | Build the core working quiz flow from user authentication through quiz completion and scoring. | Authentication; Category & Quiz Selection; Timed Quiz; Scoring & Feedback | Registration and login; quiz category display and selection; quiz selection; question and answer option display; timer; answer recording; quiz timeout; answer evaluation; instant feedback; score calculation and final score display
Sprint 2 | Complete and finalize the quiz system by adding result storage, leaderboard functionality, administrator controls, security, reliability, and compatibility. | Results & Leaderboard; Quiz Content Management; Security & Access Control; Reliability & Compatibility | Quiz result storage and reporting; leaderboard records and rankings; adding, updating, and deleting quiz questions; category management; administrator authorization; protection of credentials and sensitive data; performance and data consistency validation; browser/mobile compatibility; final integration and testing

## Sheet3
Requirement ID | Requirement | Mapped User Story | Sprint
REQ-01 | The system shall display the available quiz categories. | S1-03 – Display Quiz Categories | Sprint 1
REQ-02 | The system shall allow the user to select a quiz category. | S1-04 – Select Quiz Category | Sprint 1
REQ-03 | The system shall display the quizzes associated with the selected category. | S1-05 – Display Quizzes for Selected Category | Sprint 1
REQ-04 | The system shall display multiple-choice questions for the selected quiz. | S1-06 – Display Quiz Questions and Options | Sprint 1
REQ-05 | The system shall provide multiple answer options for each question. | S1-06 – Display Quiz Questions and Options | Sprint 1
REQ-06 | The system shall start a timer when the quiz begins. | S1-07 – Start Quiz Timer | Sprint 1
REQ-07 | The system shall record the user's selected answers. | S1-08 – Record User Answers | Sprint 1
REQ-08 | The system shall automatically end the quiz when the time limit expires. | S1-09 – End Quiz on Timeout | Sprint 1
REQ-09 | The system shall evaluate the user's submitted answers. | S1-10 – Evaluate Submitted Answers | Sprint 1
REQ-10 | The system shall provide instant feedback on the user's answers. | S1-11 – Provide Instant Feedback | Sprint 1
REQ-11 | The system shall calculate the user's score based on the number of correct answers. | S1-12 – Calculate Quiz Score | Sprint 1
REQ-12 | The system shall display the final score after quiz completion. | S1-13 – Display Final Score | Sprint 1
REQ-13 | The system shall store the user's quiz score. | S2-01 – Store Quiz Results | Sprint 2
REQ-14 | The system shall maintain leaderboard records for completed quizzes. | S2-02 – Maintain Leaderboard Records | Sprint 2
REQ-15 | The system shall display users' rankings based on quiz performance. | S2-03 – Display Leaderboard Rankings | Sprint 2
REQ-16 | The system shall allow the administrator to add quiz questions. | S2-08 – Add Quiz Questions | Sprint 2
REQ-17 | The system shall allow the administrator to update quiz questions. | S2-09 – Update Quiz Questions | Sprint 2
REQ-18 | The system shall allow the administrator to delete quiz questions. | S2-10 – Delete Quiz Questions | Sprint 2
REQ-19 | The system shall allow the administrator to manage quiz categories. | S2-11 – Manage Quiz Categories | Sprint 2
REQ-20 | The system shall provide quiz questions and user actions with minimal delay during normal operation. | S1-14 – Validate Performance and Reliable Response Handling | Sprint 1
REQ-21 | The system shall record quiz responses and scores accurately without noticeable delay. | S1-14 – Validate Performance and Reliable Response Handling | Sprint 1
REQ-22 | The system shall require authentication for access to user accounts. | S1-02 – Implement User Authentication | Sprint 1
REQ-23 | The system shall restrict administrative functions to authorized administrators. | S2-06 – Authorize Administrator Access | Sprint 2
REQ-24 | The system shall protect user credentials and sensitive information during transmission. | S2-12 – Protect Credentials and Sensitive Data | Sprint 2